ROADWORKS OCTOBER  2013
Report - to be tabled at the October 19th AGM
As per instructions from the board/community meeting in September, the following works have now been undertaken:-

Nevertire Road has received almost 400 tonnes of roadbase, grading and rolling,  from our neighbour Jason’s entrance to the Maria River Road intersection the road is in greatly improved condition. It must be said however that a great deal more will have to be spent to achieve a quality similar to Goolawah’s internal roads. 

A small amount of material is left over and stored at Jason’s for the moment and can be used next year; we were rather lucky in that the roadbase was considerably cheaper than at other times.

Internally, Forest Way is now completed all the way to the Eastern end of the village “The Bowl”. All other roads built in the last tranche in 2012 have received their final grade and roll and are in superb condition. In particular: Cockatoo Ridge, Paradise Park, Cookie Close and Waterview Lane.

Work on the internal roads amounted to just under $8,000 and on Nevertire Road to just over $18,000 – with GST added on the total is $28,500 This represents an over-run of about $3,500. Whilst this is obviously regrettable, it should be noted that a tremendous amount of work was accomplished and it is not always possible to predict final costs with absolute accuracy.  

One “culprit” were the extremely dry conditions necessitating a water truck to run the whole time work was underway – this additional cost amounted to about $800 per diem.

Furthermore, an application for a grant under the Unmaintained Roads Contribution Scheme has been lodged with Kempsey council.  The application has a reasonable chance of being successful and this injection would more than “cover” said over-run.

Future works, presumably some time in 2014, would include re-shaping the old section of Forest Way (from Russell’s East) and our old friend, Illa Langi Road.

Ralph

